## 27 june to 2july
Hottest Deal Admin - Shubhada
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-27 | None |  |  |  |  | Suspend
Tuesday | 2022-06-28 | None |  |  |  |  | Suspend
Wednesday | 2022-06-29 | Add Image in DB, icon | 2022-06-29 | 2022-06-29 | Image, icon | Complete | Complete
Thrusday | 2022-06-30 | Login Session, Add catrgory dropdown, add sub category dropdown | 2022-06-30 | 2022-06-30 | Login Session, Add catrgory dropdown, add sub category dropdown | Complete | Complete
Friday | 2022-07-01 | images | 2022-07-01 | 2022-07-01 | images
Saturday | 2022-07-02 | Holiday | 2022-07-02 | 2022-07-02
Ankita
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-27 |  | 2022-06-27 | 2022-06-27
Tuesday | 2022-06-28 |  | 2022-06-28 | 2022-06-28
Wednesday | 2022-06-29 |  | 2022-06-29 | 2022-06-29
Thrusday | 2022-06-30 |  | 2022-06-30 | 2022-06-30
Friday | 2022-07-01 |  | 2022-07-01 | 2022-07-01
Saturday | 2022-07-02 |  | 2022-07-02 | 2022-07-02
Nimble Tech - Krutanjali
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-27 | Add Content in Listing Website | 2022-06-27 | 2022-06-27 | Add Content in Listing Website | Complete | Complete
Tuesday | 2022-06-28 | Add content in I expert | 2022-06-28 | 2022-06-28 | Add content in I expert | Complete | Complete
Wednesday | 2022-06-29 | Find template and add pages in nimble tech | 2022-06-29 | 2022-06-29 | Find template and add pages in nimble tech | Complete | Complete
Thrusday | 2022-06-30 | Add Content in nimble tech complete website | 2022-06-30 | 2022-06-30 | Add Content in nimble tech complete website | Complete | Complete
Friday | 2022-07-01 | I expert, nimble tech websites | 2022-07-01 | 2022-07-01 | I expert, nimble tech websites | Complete | Complete
Saturday | 2022-07-02 | Holiday | 2022-07-02 | 2022-07-02
Error Correction in Gizmodo - Pravina
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-27 | None |  |  |  |  | Suspend
Tuesday | 2022-06-28 | None |  |  |  |  | Suspend
Wednesday | 2022-06-29 | Error correction in gizmodo | 2022-06-29 | 2022-06-29 | Error correction in gizmodo | Complete | Complete
Thrusday | 2022-06-30 | Add content and complete site. | 2022-06-30 | 2022-06-30 | Add content and complete site. | Complete | Complete
Friday | 2022-07-01 | Gizmodo error correction | 2022-07-01 | 2022-07-01 | Gizmodo error correction | Complete | Complete
Saturday | 2022-07-02 | Holiday | 2022-07-02 | 2022-07-02

## 20 to 25 June
Gizmodo/ Hottest Deal Admin - Shubhada
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-20 | Add Pages and add content | 2022-06-20 | 2022-06-20 | 2 pages should be add | Complete | Complete
Tuesday | 2022-06-21 | Add Content in pages | 2022-06-21 | 2022-06-21 | 3 pages should be add content | Incomplete | Incomplete
Wednesday | 2022-06-22 | Hottest Deal Dashboard | 2022-06-22 | 2022-06-22 | Backend Login & Register | Complete | Complete
Thrusday | 2022-06-23 | Hottest Deal Dashboard | 2022-06-23 | 2022-06-23 | Add Category/Sub-category/Items | Complete | Complete
Friday | 2022-06-24 | Hottest Deal Dashboard/Gizmodo Error Correction | 2022-06-24 | 2022-06-24 | 1.Add Session/image in DB/Category dropdown/items>Sub-category 2.Gizmodo Error Correction | Incomplete | Incomplete
Saturday | 2022-06-25 | Holiday | 2022-06-25 | 2022-06-25
Nimble Tech Website - Ankita
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-20 | Add Pages | 2022-06-20 | 2022-06-20 | Leave | Leave | Leave
Tuesday | 2022-06-21 | Add Content | 2022-06-21 | 2022-06-21 | 2 pages should be add | Complete | Complete
Wednesday | 2022-06-22 | Add Content | 2022-06-22 | 2022-06-22 | 2 pages should be add | Incomplete | Incomplete
Thrusday | 2022-06-23 | Add Content | 2022-06-23 | 2022-06-23 | Leave | Leave | Leave
Friday | 2022-06-24 | Add Content | 2022-06-24 | 2022-06-24 | Entire website should be completed till EOD | Incomplete | Incomplete
Saturday | 2022-06-25 | Holiday | 2022-06-25 | 2022-06-25
On Support - Krutanjali
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-20 | Add Content in Gizmodo | 2022-06-20 | 2022-06-20 | Add Content in Gizmodo | Complete | Complete
Tuesday | 2022-06-21 | CT Services Updates | 2022-06-21 | 2022-06-21 | CT Services Updates | Complete | Complete
Wednesday | 2022-06-22 | CT Services Updates | 2022-06-22 | 2022-06-22 | CT Services Updates | Complete | Complete
Thrusday | 2022-06-23 | Add Content in Gizmodo | 2022-06-23 | 2022-06-23 | Add Content in Gizmodo | Complete | Complete
Friday | 2022-06-24 | Listing hub Website add content | 2022-06-24 | 2022-06-24 | Add content | Complete | Complete
Saturday | 2022-06-25 | Holiday | 2022-06-25 | 2022-06-25
CT Service Register Form - Pravina
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-06-20 | Updating pages in CT Services | 2022-06-20 | 2022-06-20 | Removing Unwanted Content from the website | Complete | Complete
Tuesday | 2022-06-21 | Updating pages in CT Services | 2022-06-21 | 2022-06-21 | Removing Unwanted Content from the website | Complete | Complete
Wednesday | 2022-06-22 | Updating pages in CT Services | 2022-06-22 | 2022-06-22 | Add register form | Complete | Complete
Thrusday | 2022-06-23 | Updating pages in CT Services | 2022-06-23 | 2022-06-23 | Add Validation | Complete | Complete
Friday | 2022-06-24 | Listing hub Website add content | 2022-06-24 | 2022-06-24 | Add content | Incomplete | Incomplete
Saturday | 2022-06-25 | Holiday | 2022-06-25 | 2022-06-25

## 15 to 18 June
Gizmodo Website Redesign - Shubhada
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Wednesday | 2022-06-15 | Find template for the website create design | 2022-06-15 | 2022-06-15 | Complete | Complete | Complete
Thrusday | 2022-06-16 | Add Pages (6 pages Services)3 More added | 2022-06-16 | 2022-06-16 | Should complete 6 pages | Made changes in design | Late
Friday | 2022-06-17 | Add Content and any minor changes | 2022-06-17 | 2022-06-17 | Should be add content in website | Made Navigation bar | Late
Saturday | 2022-06-18 | Holiday | 2022-06-18 | 2022-06-18
Nimble Tech Website - Ankita
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Wednesday | 2022-06-15 | Find template for the website create design | 2022-06-15 | 2022-06-15 | On Leave | On Leave | On Leave
Thrusday | 2022-06-16 | Add Pages 5 | 2022-06-16 | 2022-06-16 | Should find template and create design and add pages | Complete 3 pages | Complete
Friday | 2022-06-17 | Add Content for whole website | 2022-06-17 | 2022-06-17 | Should be add content in website | Incomplete Task(added content but not completely | Late
Saturday | 2022-06-18 | Holiday | 2022-06-18 | 2022-06-18
Scriptika Website Update - Krutanjali
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Wednesday | 2022-06-15 | Update the 5 pages with content and images | 2022-06-15 | 2022-06-15 | Complete | Complete | Complete
Thrusday | 2022-06-16 | Update the 5 pages with content and images | 2022-06-16 | 2022-06-16 | Complete | Complete | Complete
Friday | 2022-06-17 | Editing and updating whole website and recheck for the minor correction | 2022-06-17 | 2022-06-17 | Should be add content in website | Incomplete Task(added content but not completely | Late
Saturday | 2022-06-18 | Holiday | 2022-06-18 | 2022-06-18
Convert File HTML to React Js - Pravina
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Wednesday | 2022-06-15 | Converting HTML Pages to react 10 pages | 2022-06-15 | 2022-06-15 | Complete | Complete | Complete
Thrusday | 2022-06-16 | Converting HTML Pages to react 24 pages | 2022-06-16 | 2022-06-16 | Complete | Complete | Complete
Friday | 2022-06-17 | Add Pages | 2022-06-17 | 2022-06-17 | Should be support to TL | Should be support to TL | Complete
Saturday | 2022-06-18 | Holiday | 2022-06-18 | 2022-06-18

## 4 to 9 July
Hottest Deal Admin - Shubhada
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-07-04 |  | 2022-07-04 | 2022-07-04
Tuesday | 2022-07-05 |  | 2022-07-05 | 2022-07-05
Wednesday | 2022-07-06 |  | 2022-07-06 | 2022-07-06
Thrusday | 2022-07-07 |  | 2022-07-07 | 2022-07-07
Friday | 2022-07-08 |  | 2022-07-08 | 2022-07-08
Saturday | 2022-07-09 | Holiday | 2022-07-09 | 2022-07-09
Nimble Tech - Krutanjali
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-07-04 |  | 2022-07-04 | 2022-07-04
Tuesday | 2022-07-05 |  | 2022-07-05 | 2022-07-05
Wednesday | 2022-07-06 |  | 2022-07-06 | 2022-07-06
Thrusday | 2022-07-07 |  | 2022-07-07 | 2022-07-07
Friday | 2022-07-08 |  | 2022-07-08 | 2022-07-08
Saturday | 2022-07-09 | Holiday | 2022-07-09 | 2022-07-09
Error Correction in Gizmodo - Pravina
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Monday | 2022-07-04 |  | 2022-07-04 | 2022-07-04
Tuesday | 2022-07-05 |  | 2022-07-05 | 2022-07-05
Wednesday | 2022-07-06 |  | 2022-07-06 | 2022-07-06
Thrusday | 2022-07-07 |  | 2022-07-07 | 2022-07-07
Friday | 2022-07-08 |  | 2022-07-08 | 2022-07-08
Saturday | 2022-07-09 | Holiday | 2022-07-09 | 2022-07-09

## 11 to 16 July
Amruta Task Report
Days | Date | Task | Start Date | End Date | Expected Work | Complete Work | Status
Thursday | 14/7/2022 | Read Doc. of laravel | 14/7/2022 | 14/7/2022
Tuesday | 15/7/2022 | Registration | 15/7/2022 | 15/7/2022
| 16/7/2022 | Login,Show Login Details of all students On Dashboard,delete perticuler data | 15/7/2022 | 16/7/2022
Monday | 18/7/2022 | Update Record | 18/7/2022
Tuesday | 19/7/2022 | Admin->Register,Login. | 19/7/2022