## admin dashboard
Scriptika Project Bug Report
Defect_ID	Module	Defect Description	Step To Reproduce	Expected Result	Actual Result	Created By	Assigned By	Screenshot	Execution Date	Reslove Date	status
1	login page	E-mail icon and password icon is missing	login page	icons should be present	icon is not present	shraddha			9/3/2022login page
2	login page	login table size will be same in dashboard	login page	size will be same	size of table is change	shraddha
3	dashboard	icon of project is missing in browser	1. Go to this URL - https://demo.scriptika.com/hrms/Official/indexE / 2.login in admin page / 3.browser logo	Project logo should be in browser	Project logo is not present in browser	shraddha
4	dashboard	refresh page when click on logo / Logo is not clickable or workable	1.go to url / 2.login in admin page / 3.Dashboard	refresh page when click on logo / Click on logo should be refresh page	refresh page when click on logo / Click on logo should be refresh page
5	clients	open section with same heading name	1.go to url / 2.login in admin page / 3.cilent Dashboard	all section should be open with heading	client section,leave section not open with heading

5	project	Add project is not working	1.go to url / 2.login in admin page / 3.browser logo / 4. add project		It is showing SQL error page
6	team	create team is not working	1.go to url / 2.login in admin page / 3.click on team / 4.create team		It is showing SQL error page
7	clients	clients section is not working	1.go to url / 2.login in admin page / 3.click on clients / 4.view details		404 page not found showing
8	employee	add employee section is not working	1.go to url / 2.login in admin page / 3.click on employee section / 4.add employee		It is showing SQL error page
9	attendance	Upload weekly data attendance section is not working	1.go to url / 2.login in admin page / 3.click on attendance section / 4. click on Upload weekly data		It is showing SQL error page
10	recruitment	image or logo not display	1.go to url / 2.login in admin page / 3.click on recruitment section		broken image icon show
11	recruitment	recruitment section not accessible	1.go to url / 2.login in admin page / 3.click on recruitment section		page not workable
12	learning	monthly training not workable	1.go to url / 2.login in admin page / 3.click on recruitment section / 4.click on add monthly training		It is showing SQL error page
13	seperation	submit and cancel buttons are not workable	1.go to url / 2.login in admin page / 3.click on recruitment section / 4.click on resignation request		buttons not workable
14	termination	submit and cancel buttons are not workable			buttons not workable
15	payroll	payslip submit button not workable			Submit Buttons not workable
16	payroll	add button not workable [manage salary]			It is showing SQL error page

## employee dashboard
HRMS Project Bug Report
Defect_ID	Module	Defect Description	Step To Reproduce	Expected Result	Actual Result	Created By	Assigned By	Screenshot	Execution Date	Reslove Date	status
1	login page	login table size will be same in dashboards	login page	size will be same	size of table is change	shraddha			09/03/22
2	Login Module	Forgot password link should be accessible	1. Go to this URL - https://demo.scriptika.com/hrms/Official/indexE / 2.Click on Forgot Password link	404 page not found showing	404 page not found showing	shraddha			09/03/22
3	dashboard	Logo is not clickable or workable	1.go to url / 2.login in employee page / 3.employee dashboard	refresh page when click on logo	Page is not refresh when click on logo	shraddha			09/03/22
4	dashboard	copyright aligned center	1.go to url / 2.login in admin page dashboard	copyright should be aligned center	copyright is aligned left	shraddha			09/03/22
5	dashboard [both]	sidebar icon, font and size are same	1.go to url / 2.login in admin page dashboard	sidebar icon should be same both dashboards	icon is different in dashboards	shraddha			09/03/22
6	dashboard [both]	all form needed cancel and submit button	1.go to url / 2.login in admin page	all form should be with cancel and submit button	not present cancel and submit button	shraddha			09/03/22
7	dashboard [both]	sidebar close button not working	1.go to url / 2.login in admin page	sidebar is close or	sidebar is not close	shraddha			09/03/22
8	dashboard- / Client / Leave / Learning / Performance	open section with same heading name	1.go to url / 2.login in admin page	all section should be open with heading	client section,leave section not open with heading	shraddha			09/03/22
9	timesheet	timesheet not workable [submit]	1.go to url / 2.login in employee page 3.employee dashboard / 4.click on attendance section	submit button should be workable	submit button not workable	shraddha			09/03/22
10	attendance	spelling mistake	1.go to url / 2.login in employee page / 3.employee dashboard / 4.click on attendance section	spelling should be correct “attendance”	spelling mistake of heading is incorrect	shraddha			09/03/22
11	task information	table should be in proper aligned		table should be in proper alignment		shraddha			09/03/22
12	clients	clients section is not working			404 page not found showing	shraddha			09/03/22
13	learning	spelling mistake		spelling should be correct “training ”	spelling mistake of heading is incorrect	shraddha			09/03/22
14	resignation	form input field sequence displayed in table				shraddha			09/03/22
15	resignation	Keep status column last in list				shraddha			09/03/22
16	resignation	cancel button not workable				shraddha			09/03/22
17	payroll	heading row is double in downside				shraddha			09/03/22