## Sheet1
Reliable Project
defect_ID	Pre-condition	defect description	step to reproduce	expected result	actual result	created by	assigned by	screenshot	status	execution date
1		candidate footer not necessary for employer login	1. candidate dashboard 2.candidate footer	employer login not necessary	employer login their	shraddha				26-08-2022
2		employer footer not necessary for employer login	1. employer dashboard 2.employer footer	candidate login not necessary	candidate login their	shraddha				26-08-2022
3		search tab should be center alignment	1. admin dashboard / 2.shortlisted candidate	search tab should be center	search tab is not aligned	shraddha				26-08-2022
4		ID column will be separate	1.admin dashboard / 2.requirement history	ID column be separate	two content in one column	shraddha				26-08-2022
5		ID column will be separate	1. admin dashboard / 2. click on invoice	ID column be separate	two content in one column	shraddha				26-08-2022
6		column name should be change	1.admin dashboard / 2. click on invoice / 3.click on view invoice	column name should be change [example. employee name]	item name is column name	shraddha				26-08-2022
7		quality or unit must one table will be there	1.admin dashboard / 2. click on invoice / 3.click on view invoice	quality or unit table needed	There are unit or quantity columns	shraddha				26-08-2022
8		Add Rate and amount input fields in customise invoice fornt	1.admin dashboard / 2. Go to the requirement history / 3.click on expand tavle icon(plus icon) / 4.Click on view button of shortlisted candidate	Add rate and amount input field in SGST, CGST in that invoice form	Rate and amount input fields are missing	shraddha				26-08-2022
9		spelling mistake	1.admin dashboard / 2. click on invoice / 3.click on view invoice	“ signature”	spelling wrong	shraddha				26-08-2022
10		spelling mistake in close cards on dashboard	1.admin page / 2.cards on dashboard	“close”	spelling wrong	shraddha				26-08-2022
11		spelling mistake	1.side menu heading of dashboards of employee, admin and candidate	“calendar”	admin, candidate and employer side menu heading is wrong	shraddha				26-08-2022
12		keep every dashboard previous and next button color or layout same	dashboards	same in every dashboard	various in every dashboard	shraddha				26-08-2022
13		mobile and phone no. is repeated in update profile form of employee	1.employer dashboard / 2.profile icon	mobile or phone must be one is there	There are mobile and phone no are two input fields	shraddha				26-08-2022
14		spelling mistake card of close on dashboard	1.employer page / 2.cards on dashboard	“close”	spelling wrong	shraddha				26-08-2022
15		spelling mistake	1.employer page / 2.shortlisted candidate	“received”	spelling wrong	shraddha				26-08-2022
16		Button name correction	1. employer dashboard / 2. interview history / 3.view	Button name should be “Select”	Button name is “Selected”	shraddha				26-08-2022
17		“notification” icon is must be same	dashboards	Notification icon should be same in all dashboards	different in candidate dashboard	shraddha				26-08-2022
18		salary range	1.candidate dashboard / 2.my resume in work preference	add salary range dropdown or else add from – to input fields	There is only salary from input field	shraddha				26-08-2022
19		date in – date out	1.candidate dashboard / 2.my resume	date in – date out should be lowercase, separated and with calendar icon	one textbox for date in-out	shraddha				26-08-2022
20		change the input field name	1.candidate dashboard / 2.my resume	add “designation” heading instead of title	input field name is title	shraddha				26-08-2022
21		Add color to button	1.candidate dashboard / 2.my resume	add color to “add more” button		shraddha				26-08-2022
22		replace title to	1.candidate dashboard / 2.my resume	“institute”		shraddha				26-08-2022
23		add grade textbox	1.candidate dashboard / 2.my resume	grade textbox is needed	not textbox of grade	shraddha				26-08-2022
24		replace textbox	1.candidate dashboard / 2.my resume	“start – end”	date in-out	shraddha				26-08-2022
25		spelling mistake	1.candidate dashboard / 2.my resume	“location”	spelling mistake	shraddha				26-08-2022
26		spelling mistake	1.candidate dashboard / 2.profile	“full”	spelling mistake	shraddha				26-08-2022
27		footer candidate dashboard calendar is not mention in highlight	1.candidate footer	calendar added in highlight		shraddha				26-08-2022
28		“job details” heading after submit button is is not needed	1.candidate dashboard / 2. go to latest job / 3.click on submit resume	show “successfully resume update”	show “successfully resume update” with heading field	shraddha
29		“modal title” heading after click on date is not needed	1.candidate dashboard / 2.go to calendar / 3.click on date	display content without heading field	display content with heading field	shraddha
30		Remove the right arrow [-→] after click on date	1.candidate dashboard / 2.go to calendar / 3.click on date	right arrow should not be between view button or display content	right arrow show between view button or display content	shraddha
31		“notification” icon must be same	1.candidate dashboard / 2.go to calendar / 3.click on date / 4.click on view	Notification icon should be same in all dashboards	different icon in candidate dashboard	shraddha
32		heading of input field will be employee name	1.click on the payroll / 2.click on the view payslip / 3. add payslip	title will be employee name	title be there department	shraddha