## MONTHLY BUG REPORT
MONTHLY BUG REPORT OF PROJECT
DATE	Total No Bugs	Resolve Bugs	Pending Bugs
06/09/22	11	5	6

## ADMIN
Scriptika HRMS UI Testing Bug Report
Defect Id	Module	Defect Description	Step to Reproduce	Expected Result	Actual Result	Screenshot/Video	Execution Date	Reslove Date	Status
1	Admin Profile	Admin profile page is not open					05/09/22		Pending
2	Timesheet	1.Table headers are not bold / 2.Font of the content of table are not similar as per employee dashboard					05/09/22		Pending
3	Project Creation	1.Table column name are not similar as per the project creation form		Column name should be"Project Name" and "Team Name"			05/09/22	06/09/22	complete
4	Add Project Creation	Cancel button is missing					05/09/22	06/09/22	complete
5	Clients	1.On index page heading is missing / 2.View details button is not working					05/09/22	06/09/22	complete
6	Notification	Team Name column is missing on index page of notification					05/09/22		Pending
7	Notification	Cancel button is not present on add notification form					05/09/22	06/09/22	complete
8	Recruitment	Icon is not visible					05/09/22	06/09/22	complete
9	Recruitment	Connect to Reliable button is not working					05/09/22		Pending
10	Add Employee	Password filed is missing					05/09/22		Pending
11	Attendance	Heading of index page is not correct					05/09/22		Pending